Software Development Proposal

CAOS — Multi-Agent Practice Automation Platform

Prepared for: Venture Assist / Srivatsan & Associates

Build model: AI-Accelerated Engineering (Claude Code, senior-reviewed)

Date: September 2026

This proposal covers the end-to-end development of CAOS, scoped against the agreed Feature Documentation, PRD, ER model, and ADR 0011 (Multi-Backend Bookkeeping Connector). It sets out the solution, the build approach, a realistic phased timeline, and investment required to take the platform from design-complete to production-ready.

# 1. Executive Summary

CAOS is a multi-agent automation platform for CA practices, covering document intake, GST/TDS reconciliation and compliance, client communication, working papers, and practice management — with full read/write parity across Tally and Zoho Books.

The platform is design-complete: the Feature Documentation, PRD/Sprint Plan addendum, ER model (23 entities), and connector architecture (ADR 0011) are in place. What remains is implementation.

This proposal prices that implementation using an AI-accelerated engineering model — Claude Code as the primary development tool, applied under senior technical and compliance review at every phase gate. On this model, the full 107-feature roadmap is deliverable in approximately 5 months for ₹24L–35.5L.

# 2. Background & Objectives

Manual GST/TDS compliance work is the single largest constraint on practice growth: reconciliation, document chasing, and filing prep alone consume roughly 10 hours per client per month at a typical mid-size engagement, capping how many clients a fixed team can serve.

A mid-project discovery — that a significant share of the client base runs Zoho Books alongside or instead of Tally — expanded the platform's scope from single-backend to full dual-backend read/write parity, which is now reflected across the architecture, data model, and feature backlog.

## Objectives

- Automate the highest-time-cost workflows (reconciliation, intake, TDS, bank reconciliation) while keeping every judgment call — mismatches, exceptions, client-facing tone — in front of the auditor or staff member responsible for it

- Support Tally and Zoho Books clients on one platform, without a second product or a degraded experience for either backend

- Give the practice visibility into its own capacity, so automation gains translate into more clients served, not just faster busywork

# 3. Proposed Solution: The CAOS Platform

## Platform core

- Task engine and dashboard — the shared system every agent and every staff member works from

- BooksConnector interface with a TallyAdapter and a ZohoAdapter, so agents read/write against either backend through one contract (ADR 0011)

- Design B ("Capacity") UI system in teal/amber, applied consistently across all client- and staff-facing surfaces

## Agent suite (in scope for this proposal)

- Document Intake Agent — classification, OCR extraction, auto-filing, pending-document reminders

- Reconciliation Agent — GSTR-2A/2B vs purchase register matching, exception routing

- Validation/Compliance Agent — pre-filing checks across GSTR-1/3B, HSN codes, tax rates, TDS

- Client Communication Agent — templated reminders, judgment-gated query drafting

- Bookkeeping/Voucher Entry Agent — automated entry from client source documents into Tally or Zoho Books

- TDS/TCS Return Automation — 24Q/26Q/27EQ matching and quarterly return prep

- Bank Reconciliation Agent — statement-to-books auto-matching with exception review

- Working Paper Agent — auto-populated engagement documentation

- Practice Management Agent — capacity, workload, and billing visibility across the firm

The Notice/Scrutiny Tracker Agent and the Phase-2 value-adds (Financial Statement Analysis, ROC Tracker, Fixed Asset Register, Audit Sampling, Knowledge Base Assistant) are addressed under Out of Scope.

# 4. Scope of Work

Scope is drawn directly from the agreed feature backlog: 107 features, MoSCoW-prioritized across Phase 0–4, built on a 23-entity data model spanning the Core Platform and Compliance/Billing domains.

| Phase | Modules Delivered |
| --- | --- |
| Phase 0 | Development readiness: architecture, environment, and standards gap closure |
| Phase 1 | Task engine, dashboard, BooksConnector (Tally + Zoho adapters), Document Intake Agent |
| Phase 2 | Bookkeeping/Voucher Entry Agent, Client Communication Agent |
| Phase 3 | Reconciliation Agent, Validation/Compliance Agent, TDS/TCS Return Automation |
| Phase 4 | Bank Reconciliation Agent, Working Paper Agent, Practice Management reporting |

# 5. Development Methodology — AI-Accelerated Engineering

The platform is built with Claude Code as the primary implementation tool, used by senior engineers rather than as a lightly-used aid — it drafts, scaffolds, and implements against the agreed architecture, and every output is reviewed before it merges. This is what makes the timeline in Section 6 realistic rather than optimistic:

| Type of Work | Effect of AI-Accelerated Development |
| --- | --- |
| Boilerplate, scaffolding, CRUD & API layers | Compresses sharply — largely automated under review |
| Dual-backend connector parity (Tally ↔ Zoho) | Compresses sharply — second adapter reuses the proven pattern |
| First-draft agent logic (matching, OCR wiring, templated comms) | Compresses significantly — faster first pass, same review bar |
| GST/TDS correctness review & compliance validation | Unchanged — requires senior human sign-off regardless of tooling |
| Security review, edge-case handling, production hardening | Unchanged — same standard, same effort |

Where the review discipline sits Every phase ends at a sign-off gate, not just a code-complete date. Phase 3 (the compliance layer) carries the heaviest review load in the project — AI-accelerated code is faster to draft, not faster to certify correct against a client's actual GSTR and TDS filings.

# 6. Implementation Timeline & Phases

Total elapsed time: approximately 22 weeks (~5 months) from Phase 0 kickoff to handover, assuming timely client-side inputs (Tally Cloud access, Zoho OAuth credentials, UAT turnaround).

| Phase | Duration | Exit Criteria |
| --- | --- | --- |
| Phase 0 — Baseline & Readiness | Weeks 1–2 | Dev Readiness Checklist signed off; API Spec, Coding Guidelines, Security Standard, and Testing Strategy updated for dual-backend |
| Phase 1 — Foundation | Weeks 3–7 | Task engine + dashboard live in staging; BooksConnector passes read/write parity tests on both adapters; Intake Agent classifying real sample documents |
| Phase 2 — Leverage Agents | Weeks 8–11 | Bookkeeping Agent posts verified entries to a pilot client's books; Client Communication Agent sending reviewed reminders |
| Phase 3 — Compliance Layer | Weeks 12–17 | Reconciliation, Validation, and TDS/TCS agents pass parallel-run testing against a completed manual filing cycle |
| Phase 4 — Remaining Agents | Weeks 18–20 | Bank Reconciliation and Working Paper agents live; Practice Management dashboard reporting real firm data |
| UAT & Handover | Weeks 21–22 | Client sign-off on acceptance criteria; production cutover; team handover and documentation delivered |

Phases run sequentially at the platform-core level (each depends on the one before it), but within Phase 1 the ZohoAdapter build starts as soon as the BooksConnector interface and TallyAdapter are proven — the second adapter does not wait for the first to fully close out, which is where part of the timeline compression in Section 5 shows up directly.

# 7. Team & Engagement Model

| Role | Allocation | Responsibility |
| --- | --- | --- |
| Tech Lead / Architect | Full-time | Architecture ownership, Claude Code-driven implementation, phase-gate sign-off |
| Senior Engineer | Full-time | Agent implementation, connector work, code review |
| QA / Compliance Reviewer | Part-time, scaling up in Phase 3 | Correctness review on reconciliation/validation/TDS logic before any client-facing use |
| Project Manager | Part-time | Phase tracking, client communication, UAT coordination |

# 8. Investment (AI-Accelerated Development)

| Phase | Investment |
| --- | --- |
| Phase 0 — Baseline & Readiness | ₹1.5L – ₹2.5L |
| Phase 1 — Foundation | ₹6L – ₹9L |
| Phase 2 — Leverage Agents | ₹5L – ₹8L |
| Phase 3 — Compliance Layer | ₹7L – ₹10L |
| Phase 4 — Remaining Agents | ₹4L – ₹6L |

Total: ₹24L – ₹35.5L  (~$29K–$43K)

## Payment schedule

- 20% of total contract value on signing, to mobilize Phase 0

- Remainder invoiced at each phase's exit gate, at that phase's price from the table above

- No phase beyond Phase 0 is committed or invoiced until the prior phase's exit criteria are signed off

## Not included in this investment

- Recurring hosting, database, backup, OCR, and AI/LLM usage costs — detailed separately in Section 9

- Zoho/Tally license fees — these remain the client's existing subscription

- Ongoing support or maintenance after handover — quoted separately if required

# 9. Recurring Operating Costs (Post-Launch)

The investment in Section 8 is a one-time build cost. Running CAOS in production carries its own monthly cost — hosting, database, backups, document processing, and AI/LLM usage — which is separate from and continues after the development engagement. The figures below are built from verified provider pricing (Sept 2026), sized at target scale (~500 clients, no support/maintenance retainer included, communications email-only), and reflect the LLM cost optimizations adopted in ADR 0012.

## Fixed infrastructure (verified, volume-independent)

| Component | Basis | Monthly (₹) |
| --- | --- | --- |
| Database & backend (Supabase Pro + Medium compute) | $25 Pro + $60 compute + overage | ₹9,025 – ₹9,975 |
| App/agent hosting (Railway Pro) | $20/seat + usage | ₹4,750 – ₹8,550 |
| Email (AWS SES) | $0.10/1,000 emails, ~10–15K/mo | ₹190 – ₹475 |
| Daily backups | Included free (Supabase Pro) | ₹0 |

## Usage-driven (modeled from 75 documents/client/month)

| Component | Basis | Monthly (₹) |
| --- | --- | --- |
| OCR / document extraction | 37,500 docs/mo — 60% invoices/receipts, 40% bank statement pages (AWS Textract) — unaffected by ADR 0012 | ₹33,250 – ₹57,000 |
| AI/LLM — ramp-up (client's first 1–2 months) | Uniform LLM-per-action before vendor templates build up — the pre-ADR 0012 baseline | ₹28,500 – ₹47,500 |
| AI/LLM — steady state (month 3+) | Post ADR 0012: 4 of 9 agents off LLM entirely, Bookkeeping template-cached, prompt caching applied | ₹4,000 – ₹17,000 |

## LLM cost optimization (ADR 0012)

The original LLM estimate assumed every agent action on every document triggers a call — which scales linearly with client count. ADR 0012 removes that assumption for the agents that don't need it, and caches the ones that do:

| Agent | LLM treatment under ADR 0012 |
| --- | --- |
| Reconciliation | Off LLM entirely — deterministic GSTIN/invoice/amount matching |
| Validation / Compliance | Off LLM entirely — arithmetic comparisons and table lookups |
| TDS/TCS matching | Off LLM entirely — deterministic matching, same logic as Reconciliation |
| Bank Reconciliation | Off LLM entirely — deterministic matching by date/amount/reference |
| Bookkeeping / Voucher Entry | Reduced — vendor template caching; only new vendors or layout changes need a fresh LLM pass |
| Document Intake | Reduced — known senders route via table lookup; LLM only classifies new senders |
| Client Communication | Unchanged — genuine judgment/drafting, but model-routed (Sonnet only on an explicit confidence flag) |
| Working Paper | Reduced — mostly templated assembly |
| Practice Management | Off LLM entirely — reporting and dashboarding only |

Total (ramp-up, months 1–2 per client): ₹76,000 – ₹1,23,500/month  (~$800–$1,300)  —  ₹9.1L – ₹14.8L/year

Total (steady state, month 3+): ₹51,500 – ₹92,500/month  (~$540–$975)  —  ₹6.2L – ₹11.1L/year

What's verified vs. modeled Hosting, database, backups, email, and OCR are verified vendor rates at a tight range regardless of usage. The steady-state LLM range reflects ADR 0012's mechanisms (deterministic agents, template caching, prompt caching) but is a directional re-allocation, not a vendor-metered number — ADR 0012 itself calls this a decision record, not an updated cost model. Actual call volume, the vendor-repeat rate that drives Bookkeeping's cache hit rate, and the deterministic-vs-LLM split all need to be verified in Phase 0/1 before this range is locked in.

## Recurring cost assumptions

- 500 active clients, averaging 75 source documents/client/month (midpoint of the 50–100 range confirmed for this estimate)

- Document mix: 60% invoices/receipts, 40% bank statement pages — different OCR API tiers apply to each

- Daily backups (free, included in Supabase Pro) are sufficient recovery; no continuous point-in-time-recovery add-on

- Communications are email-only via AWS SES; no WhatsApp/SMS costs

- LLM cost reflects ADR 0012: 4 of 9 agents run deterministically with no LLM call; Bookkeeping uses vendor template caching after each vendor's first occurrence; remaining calls use prompt caching and Haiku-by-default/Sonnet-on-flag routing

- Ramp-up period (client's first 1–2 months) runs closer to the pre-optimization baseline, since vendor templates haven't built up yet — steady state is reached as the client base matures

- No support/maintenance retainer is included — this is infrastructure and third-party usage cost only

- Excludes Tally/Zoho Books license fees — these remain the client's existing subscription

- USD–INR conversion at ~₹95/USD (Sept 2026); this line moves with FX and should be re-checked periodically

- Costs assume steady-state production at target scale; pilot-scale (~100 clients) costs would be roughly 20–25% of this total, dominated by the fixed infrastructure floor rather than usage

# 10. Assumptions & Dependencies

- Tally Cloud access and Zoho Books OAuth/sandbox credentials are made available before Phase 1 begins

- A pilot client (or sanitized representative data) is available for Phase 2–4 testing against real bookkeeping and filing scenarios

- UAT feedback at each phase gate is turned around within 3 business days to hold the Section 6 timeline

- The four Tally-only assumption gaps flagged in the current documentation (API Specification, Coding Guidelines, Security Standard, Testing Strategy) are closed in Phase 0, ahead of Phase 1 build start

# 11. Out of Scope

The following are deliberately excluded from this proposal's price and timeline, consistent with the current roadmap:

- Notice/Scrutiny Tracker Agent

- Financial Statement Analysis / Ratio Agent, ROC/Companies Act Compliance Tracker, Fixed Asset Register & Depreciation Agent, Audit Sampling & Risk-Scoring Agent, Knowledge Base/Query Assistant

- Any AI-assisted audit tooling beyond the agents listed in Section 3

These can be scoped and priced as a Phase 5 addendum once the core platform is live and adoption data is available to prioritize them.

# 12. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Client-side delays (credential access, UAT turnaround) slip the Section 6 timeline | Phase gates are explicit in the contract; slippage on client-side dependencies extends the timeline without penalty to either party |
| Compliance-layer defects reach production | Phase 3 carries dedicated QA/compliance review capacity and a parallel-run test against a completed manual filing cycle before go-live |
| Zoho/Tally API changes during the build | BooksConnector's adapter pattern isolates backend-specific changes to a single adapter, not the core platform |

# 13. Next Steps & Acceptance

1.  Review this proposal against the agreed Feature Documentation and PRD scope

2.  Confirm the Phase 0 start date and named points of contact for credentials and UAT

3.  Sign off below to authorize Phase 0 mobilization

|  | Venture Assist / Srivatsan & Associates | Development Team |
| --- | --- | --- |
| Name |  |  |
| Signature |  |  |
| Date |  |  |