Software Development Proposal

CAOS — Multi-Agent Practice Automation Platform

Prepared for: Venture Assist / Srivatsan & Associates

Build model: AI-Accelerated Engineering (Claude Code, senior-reviewed)

Date: September 2026

This proposal covers the end-to-end development of CAOS, scoped against the agreed Feature Documentation, PRD, ER model, and ADR 0011 (Multi-Backend Bookkeeping Connector). It sets out the solution, the build approach, a realistic phased timeline, and investment required to take the platform from design-complete to production-ready.

# 1. Executive Summary

CAOS is a multi-agent automation platform for CA practices, covering document intake, GST/TDS reconciliation and compliance, client communication, working papers, and practice management — with full read/write parity across Tally and Zoho Books.

The platform is design-complete: the Feature Documentation, PRD/Sprint Plan addendum, ER model (23 entities), and connector architecture (ADR 0011) are in place. What remains is implementation.

This proposal prices that implementation using an AI-accelerated engineering model — Claude Code as the primary development tool, applied under senior technical and compliance review at every phase gate. On this model, the full 107-feature roadmap is deliverable in approximately 5 months for a fixed price of ₹15,00,000, plus applicable GST.

# 2. Background & Objectives

Manual GST/TDS compliance work is the single largest constraint on practice growth: reconciliation, document chasing, and filing prep alone consume roughly 10 hours per client per month at a typical mid-size engagement, capping how many clients a fixed team can serve.

A mid-project discovery — that a significant share of the client base runs Zoho Books alongside or instead of Tally — expanded the platform's scope from single-backend to full dual-backend read/write parity, which is now reflected across the architecture, data model, and feature backlog.

## Objectives

- Automate the highest-time-cost workflows (reconciliation, intake, TDS, bank reconciliation) while keeping every judgment call — mismatches, exceptions, client-facing tone — in front of the auditor or staff member responsible for it

- Support Tally and Zoho Books clients on one platform, without a second product or a degraded experience for either backend

- Give the practice visibility into its own capacity, so automation gains translate into more clients served, not just faster busywork

# 3. Proposed Solution: The CAOS Platform

## Platform core

- Task engine and dashboard — the shared system every agent and every staff member works from

- BooksConnector interface with a TallyAdapter and a ZohoAdapter, so agents read/write against either backend through one contract (ADR 0011)

- Design B ("Capacity") UI system in teal/amber, applied consistently across all client- and staff-facing surfaces

## Agent suite (in scope for this proposal)

- Document Intake Agent — classification, OCR extraction, auto-filing, pending-document reminders

- Reconciliation Agent — GSTR-2A/2B vs purchase register matching, exception routing

- Validation/Compliance Agent — pre-filing checks across GSTR-1/3B, HSN codes, tax rates, TDS

- Client Communication Agent — templated reminders, judgment-gated query drafting

- Bookkeeping/Voucher Entry Agent — automated entry from client source documents into Tally or Zoho Books

- TDS/TCS Return Automation — 24Q/26Q/27EQ matching and quarterly return prep

- Bank Reconciliation Agent — statement-to-books auto-matching with exception review

- Working Paper Agent — auto-populated engagement documentation

- Practice Management Agent — capacity, workload, and billing visibility across the firm

The Notice/Scrutiny Tracker Agent and the Phase-2 value-adds (Financial Statement Analysis, ROC Tracker, Fixed Asset Register, Audit Sampling, Knowledge Base Assistant) are addressed under Out of Scope.

# 4. Scope of Work

Scope is drawn directly from the agreed feature backlog: 107 features, MoSCoW-prioritized across Phase 0–4, built on a 23-entity data model spanning the Core Platform and Compliance/Billing domains.

| Phase | Modules Delivered |
| --- | --- |
| Phase 0 | Development readiness: architecture, environment, and standards gap closure |
| Phase 1 | Task engine, dashboard, BooksConnector (Tally + Zoho adapters), Document Intake Agent |
| Phase 2 | Bookkeeping/Voucher Entry Agent, Client Communication Agent |
| Phase 3 | Reconciliation Agent, Validation/Compliance Agent, TDS/TCS Return Automation |
| Phase 4 | Bank Reconciliation Agent, Working Paper Agent, Practice Management reporting |

# 5. Development Methodology — AI-Accelerated Engineering

The platform is built with Claude Code as the primary implementation tool, used by senior engineers rather than as a lightly-used aid — it drafts, scaffolds, and implements against the agreed architecture, and every output is reviewed before it merges. This is what makes the timeline in Section 6 realistic rather than optimistic:

| Type of Work | Effect of AI-Accelerated Development |
| --- | --- |
| Boilerplate, scaffolding, CRUD & API layers | Compresses sharply — largely automated under review |
| Dual-backend connector parity (Tally ↔ Zoho) | Compresses sharply — second adapter reuses the proven pattern |
| First-draft agent logic (matching, OCR wiring, templated comms) | Compresses significantly — faster first pass, same review bar |
| GST/TDS correctness review & compliance validation | Unchanged — requires senior human sign-off regardless of tooling |
| Security review, edge-case handling, production hardening | Unchanged — same standard, same effort |

Where the review discipline sits Every phase ends at a sign-off gate, not just a code-complete date. Phase 3 (the compliance layer) carries the heaviest review load in the project — AI-accelerated code is faster to draft, not faster to certify correct against a client's actual GSTR and TDS filings.

# 6. Implementation Timeline & Phases

Total elapsed time: approximately 22 weeks (~5 months) from Phase 0 kickoff to handover, assuming timely client-side inputs (Tally Cloud access, Zoho OAuth credentials, UAT turnaround).

| Phase | Duration | Exit Criteria |
| --- | --- | --- |
| Phase 0 — Baseline & Readiness | Weeks 1–2 | Dev Readiness Checklist signed off; API Spec, Coding Guidelines, Security Standard, and Testing Strategy updated for dual-backend |
| Phase 1 — Foundation | Weeks 3–7 | Task engine + dashboard live in staging; BooksConnector passes read/write parity tests on both adapters; Intake Agent classifying real sample documents |
| Phase 2 — Leverage Agents | Weeks 8–11 | Bookkeeping Agent posts verified entries to a pilot client's books; Client Communication Agent sending reviewed reminders |
| Phase 3 — Compliance Layer | Weeks 12–17 | Reconciliation, Validation, and TDS/TCS agents pass parallel-run testing against a completed manual filing cycle |
| Phase 4 — Remaining Agents | Weeks 18–20 | Bank Reconciliation and Working Paper agents live; Practice Management dashboard reporting real firm data |
| UAT & Handover | Weeks 21–22 | Client sign-off on acceptance criteria; production cutover; team handover and documentation delivered |

Phases run sequentially at the platform-core level (each depends on the one before it), but within Phase 1 the ZohoAdapter build starts as soon as the BooksConnector interface and TallyAdapter are proven — the second adapter does not wait for the first to fully close out, which is where part of the timeline compression in Section 5 shows up directly.

# 7. Team & Engagement Model

| Role | Allocation | Responsibility |
| --- | --- | --- |
| Tech Lead / Architect | Full-time | Architecture ownership, Claude Code-driven implementation, phase-gate sign-off |
| Senior Engineer | Full-time | Agent implementation, connector work, code review |
| QA / Compliance Reviewer | Part-time, scaling up in Phase 3 | Correctness review on reconciliation/validation/TDS logic before any client-facing use |
| Project Manager | Part-time | Phase tracking, client communication, UAT coordination |

# 8. Investment (AI-Accelerated Development)

The development engagement is offered at a fixed price of ₹15,00,000 (Rupees Fifteen Lakh only), exclusive of GST. This covers all work in Phases 0–4 (Section 4), UAT, production go-live, training, and the 120-day post-go-live warranty.

## Payment schedule

| Milestone | Trigger | Amount |
| --- | --- | --- |
| M1: Acceptance | Signed acceptance of this proposal | ₹2,00,000 |
| M2: UAT deployment | Platform deployed to the UAT environment with the full Phase 0–4 scope available for client testing | ₹4,00,000 |
| M3: Go-live | Production cutover, with the platform live for the practice's use | ₹4,00,000 |
| M4: Stabilisation close | 30 days after go-live | ₹5,00,000 |
| Total |  | ₹15,00,000 |

## Payment terms

- Each milestone is invoiced when it is achieved and is payable within 7 days of the invoice date. GST at the prevailing rate (currently 18%) is charged in addition.

- UAT acceptance. The client has 10 business days from UAT deployment to test against the agreed acceptance criteria. Only Severity 1 or Severity 2 defects (Section 10.1) block acceptance. Severity 3 and 4 defects are logged and fixed during the warranty period.

- M4 release. The M4 payment is released 30 days after go-live, provided no Severity 1 defect attributable to the development team remains open.

- Schedule changes. If UAT or go-live is delayed for reasons outside the development team's control, both parties will agree a revised date in good faith. Milestone invoicing will be aligned to that revised date.

- Change requests. Approved change requests (Section 10.6) are priced separately and do not alter the milestone amounts above.

- Licence and ownership. Covered in Section 10.7.

## Not included in this investment

- Recurring hosting, database, backup, OCR, and AI/LLM usage costs, detailed in Section 9

- Zoho/Tally license fees, which remain the client's existing subscription

- Support after the 120-day warranty period, available on request under a separate agreement

- Items listed under Out of Scope (Section 12)

# 9. Recurring Operating Costs (Post-Launch)

The investment in Section 8 is a one-time build cost. Running CAOS in production carries its own monthly cost — hosting, database, backups, document processing, and AI/LLM usage — which is separate from and continues after the development engagement. The figures below are built from verified provider pricing (Sept 2026), sized at target scale (~500 clients, no support/maintenance retainer included, communications email-only), and reflect the LLM cost optimizations adopted in ADR 0012.

## Fixed infrastructure (verified, volume-independent)

| Component | Basis | Monthly (₹) |
| --- | --- | --- |
| Database & backend (Supabase Pro + Medium compute) | $25 Pro + $60 compute + overage | ₹9,025 – ₹9,975 |
| App/agent hosting (Railway Pro) | $20/seat + usage | ₹4,750 – ₹8,550 |
| Email (AWS SES) | $0.10/1,000 emails, ~10–15K/mo | ₹190 – ₹475 |
| Daily backups | Included free (Supabase Pro) | ₹0 |

## Usage-driven (modeled from 75 documents/client/month)

| Component | Basis | Monthly (₹) |
| --- | --- | --- |
| OCR / document extraction | 37,500 docs/mo — 60% invoices/receipts, 40% bank statement pages (AWS Textract) — unaffected by ADR 0012 | ₹33,250 – ₹57,000 |
| AI/LLM — ramp-up (client's first 1–2 months) | Uniform LLM-per-action before vendor templates build up — the pre-ADR 0012 baseline | ₹28,500 – ₹47,500 |
| AI/LLM — steady state (month 3+) | Post ADR 0012: 4 of 9 agents off LLM entirely, Bookkeeping template-cached, prompt caching applied | ₹4,000 – ₹17,000 |

## LLM cost optimization (ADR 0012)

The original LLM estimate assumed every agent action on every document triggers a call — which scales linearly with client count. ADR 0012 removes that assumption for the agents that don't need it, and caches the ones that do:

| Agent | LLM treatment under ADR 0012 |
| --- | --- |
| Reconciliation | Off LLM entirely — deterministic GSTIN/invoice/amount matching |
| Validation / Compliance | Off LLM entirely — arithmetic comparisons and table lookups |
| TDS/TCS matching | Off LLM entirely — deterministic matching, same logic as Reconciliation |
| Bank Reconciliation | Off LLM entirely — deterministic matching by date/amount/reference |
| Bookkeeping / Voucher Entry | Reduced — vendor template caching; only new vendors or layout changes need a fresh LLM pass |
| Document Intake | Reduced — known senders route via table lookup; LLM only classifies new senders |
| Client Communication | Unchanged — genuine judgment/drafting, but model-routed (Sonnet only on an explicit confidence flag) |
| Working Paper | Reduced — mostly templated assembly |
| Practice Management | Off LLM entirely — reporting and dashboarding only |

Total (ramp-up, months 1–2 per client): ₹76,000 – ₹1,23,500/month  (~$800–$1,300)  —  ₹9.1L – ₹14.8L/year

Total (steady state, month 3+): ₹51,500 – ₹92,500/month  (~$540–$975)  —  ₹6.2L – ₹11.1L/year

What's verified vs. modeled Hosting, database, backups, email, and OCR are verified vendor rates at a tight range regardless of usage. The steady-state LLM range reflects ADR 0012's mechanisms (deterministic agents, template caching, prompt caching) but is a directional re-allocation, not a vendor-metered number — ADR 0012 itself calls this a decision record, not an updated cost model. Actual call volume, the vendor-repeat rate that drives Bookkeeping's cache hit rate, and the deterministic-vs-LLM split all need to be verified in Phase 0/1 before this range is locked in.

## Recurring cost assumptions

- 500 active clients, averaging 75 source documents/client/month (midpoint of the 50–100 range confirmed for this estimate)

- Document mix: 60% invoices/receipts, 40% bank statement pages — different OCR API tiers apply to each

- Daily backups (free, included in Supabase Pro) are sufficient recovery; no continuous point-in-time-recovery add-on

- Communications are email-only via AWS SES; no WhatsApp/SMS costs

- LLM cost reflects ADR 0012: 4 of 9 agents run deterministically with no LLM call; Bookkeeping uses vendor template caching after each vendor's first occurrence; remaining calls use prompt caching and Haiku-by-default/Sonnet-on-flag routing

- Ramp-up period (client's first 1–2 months) runs closer to the pre-optimization baseline, since vendor templates haven't built up yet — steady state is reached as the client base matures

- No support/maintenance retainer is included — this is infrastructure and third-party usage cost only

- Excludes Tally/Zoho Books license fees — these remain the client's existing subscription

- USD–INR conversion at ~₹95/USD (Sept 2026); this line moves with FX and should be re-checked periodically

- Costs assume steady-state production at target scale; pilot-scale (~100 clients) costs would be roughly 20–25% of this total, dominated by the fixed infrastructure floor rather than usage

# 10. Support, Training, Warranty & Licensing

## 10.1 Defect severity and service levels

| Severity | Definition | Response | Resolution / workaround |
| --- | --- | --- | --- |
| S1: Critical | Platform unavailable, data loss or corruption, incorrect postings to Tally/Zoho, or compliance output producing wrong filing figures. No workaround exists. | 2 business hours | 1 business day |
| S2: High | A major agent or function is impaired, but a workaround exists | 4 business hours | 3 business days |
| S3: Medium | Minor function or UI issue affecting normal use | 1 business day | 10 business days or next release |
| S4: Low | Cosmetic issue or documentation error | 2 business days | Scheduled release |

Filing-deadline cover. On statutory due dates (GSTR-1, GSTR-3B, and quarterly TDS/TCS returns), S1 support is extended to 21:00 IST, including when a due date falls on a Sunday or holiday.

Support channel. Support is provided through email or a ticketing tool, with a named point of contact on each side. Hours are Monday to Saturday, 10:00–19:00 IST, excluding national holidays. S1 issues may also be raised by phone.

## 10.2 Warranty (120 days from go-live)

For 120 days from go-live, the development team provides the following at no additional cost:

- Defect fixes. Any defect is fixed according to the service levels in 10.1. A defect means a deviation from the agreed Feature Documentation, PRD, or accepted UAT criteria.

- Hosting support, as described in 10.4.

- Minor enhancements, as defined in 10.5, handled on a reasonable-effort basis.

- Minor statutory updates. Examples include a GST or TDS rate change, or a small field or format change in a return.

- Stabilisation support. For the first 30 days after go-live, this includes daily monitoring, priority defect fixing, and on-call support for the practice's staff.

The warranty does not cover:

- changes made to the code or configuration by anyone other than the development team

- outages in third-party services (AWS, Zoho, Tally, the GSTN portal)

- issues arising from incorrect source data

Where such an issue affects the practice, the development team will still assist in diagnosing it and restoring normal operation.

## 10.3 Training

Training is included in the fixed price:

- Administrator training. Platform configuration, user management, and connector setup for Tally and Zoho.

- Staff training. Day-to-day use of each agent, reviewing exceptions, and approving outputs. Up to 4 sessions are delivered online or at the client's office.

- Documentation. User guides for each agent and an administrator manual, delivered at go-live.

- Recorded walkthroughs of key workflows, for onboarding new staff.

- Refresher session. One session within the warranty period, typically ahead of the first quarterly TDS cycle after go-live.

## 10.4 Hosting support

The platform runs in a dedicated AWS account held in the client's name, and AWS charges are paid directly by the client (Section 9).

During the warranty period, the development team administers the environment, covering:

- monitoring and alerting

- daily backup verification and restores on request

- security patching

- SSL and domain management

- incident response under 10.1

After the warranty period, hosting support is available under a separate agreement.

## 10.5 Minor enhancements

A minor enhancement is a change to an existing feature that meets all of these conditions:

- it takes roughly 2 working days of effort or less

- it adds no new agent, integration, or data entity

- it does not change the data model or architecture

Examples include a new report column, an email template change, a validation rule adjustment, a new document-type mapping, or a dashboard filter.

## 10.6 Major features and change requests

Anything beyond the minor enhancement definition is a change request. This includes new agents (including the Out of Scope items in Section 12), new integrations, data model changes, and multi-firm capability.

Change requests follow this process:

1.  The client submits a written request.

2.  Within 5 business days, the development team provides an impact assessment covering effort, cost, timeline, and risk.

3.  Work is scheduled after the client's written approval.

4.  Depending on the quantum of work, it is billed at ₹12,000 per person-day or on a fixed-cost basis through a separate proposal.

During the build, scope is frozen to Section 4 on acceptance of this proposal. Change requests raised during the build follow the same process and may extend the Section 6 timeline.

As the first client on the platform, Venture Assist / Srivatsan & Associates will receive preferential pricing on change requests and post-warranty support.

## 10.7 Licence and ownership

- Client licence. On receipt of the M4 payment, the client receives a perpetual, royalty-free licence to use the CAOS platform for its own practice and its clients. The licence is non-exclusive and non-transferable, and does not extend to resale, sublicensing, or use by other firms. The CAOS platform remains the property of the development team, which continues to develop it as a product.

- Source code. Source code of the deployed version will be made available to the client under the terms of this licence.

- Client data and confidentiality. All client data belongs to the client. This covers practice data, client records, documents, filings, and firm-specific configurations and templates. None of it will be used for, or disclosed to, any other customer. Firm-specific business rules or workflows shared by the practice are treated as confidential.

# 11. Assumptions & Dependencies

- Tally Cloud access and Zoho Books OAuth/sandbox credentials are made available before Phase 1 begins

- A pilot client (or sanitized representative data) is available for Phase 2–4 testing against real bookkeeping and filing scenarios

- UAT feedback at each phase gate is turned around within 3 business days to hold the Section 6 timeline

- The four Tally-only assumption gaps flagged in the current documentation (API Specification, Coding Guidelines, Security Standard, Testing Strategy) are closed in Phase 0, ahead of Phase 1 build start

# 12. Out of Scope

The following are deliberately excluded from this proposal's price and timeline, consistent with the current roadmap:

- Notice/Scrutiny Tracker Agent

- Financial Statement Analysis / Ratio Agent, ROC/Companies Act Compliance Tracker, Fixed Asset Register & Depreciation Agent, Audit Sampling & Risk-Scoring Agent, Knowledge Base/Query Assistant

- Any AI-assisted audit tooling beyond the agents listed in Section 3

These can be scoped and priced as a Phase 5 addendum once the core platform is live and adoption data is available to prioritize them.

# 13. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Client-side delays (credential access, UAT turnaround) slip the Section 6 timeline | Phase gates are explicit in the contract; slippage on client-side dependencies extends the timeline without penalty to either party. Payment milestones follow the schedule-changes clause in Section 8. |
| Compliance-layer defects reach production | Phase 3 carries dedicated QA/compliance review capacity and a parallel-run test against a completed manual filing cycle before go-live |
| Zoho/Tally API changes during the build | BooksConnector's adapter pattern isolates backend-specific changes to a single adapter, not the core platform |

# 14. Next Steps & Acceptance

1.  Review this proposal against the agreed Feature Documentation and PRD scope

2.  Confirm the Phase 0 start date and named points of contact for credentials and UAT

3.  Sign off below to accept this proposal and authorise Phase 0 mobilisation (milestone M1).

|  | Venture Assist / Srivatsan & Associates | Development Team |
| --- | --- | --- |
| Name |  |  |
| Signature |  |  |
| Date |  |  |